## Sheet1
Completed | Tasks | DeadLine | Duration | Actual Duration
Done | Setup directory and ORM and databases | 17/4 | 1 | 2
| Setup Authorization with Resend API | 21/4 | 2
| Option to CRUD yarn contracts with weight and other details. (unit conversion applied automatically) | 23/4 | 3
| Display those yarns at third-party locations and those received. | 23/4 | 3
| Option to CRUD BOM for each contract. There will be a contract lookup in this BOM. | 24/4 | 3
| Show the total cost using the math, for each contract in the metrics. Automated process. | 25/4 | 5
| Option to CRUD Challans for greige fabric, with wastage and consumption. | 25/4 | 3
| Show the Variance on metrics for the greige fabric. | 26/4 | 7
| Option to CRUD Dyeing Units. Automatically calculate average weight reduction | 27/4 | 3
| total yarn issued against total fabric received plus agreed wastage (typically 3.5%) | 28/4 | 3
| Graphs for visualization. | 29/4 | 7
| Testing | 2026-01-05 | 15